

**Town of Speedway
Arts Council**

**Meeting on 7/14/2022**

**In Attendance:**

**Katie Maiers, Bruce Levy, Chris Nusbaum, Cheryl McElroy**

# **Active Projects**

**SMC Mural**

* **Proposal/Update: Bruce and Chris**
	+ Photo Storage
	+ Forms for public to opt in to arts using photos
* **Discussion:**
	+ Online submissions/form to opt in and submit pics and give rights for Arts council to use photos
	+ IMS Permission to use photos
* **Decisions**: N/A
* **Next Steps:**
	+ Katie to reach out to IMS Photo Lab, Bruce to create online submission platform

**Community Mural**

* **Proposal/Update: Katie**
	+ 10 gallons of clear coat from PPG was bad and we could not use
* **Discussion:**
	+ We need to apply Rain Guard product K7000
		- Cost: $188 per 5 gallons
* **Decisions**:
	+ Chris made motion for a $500 budget to purchase RainGuard product and rolling supplies to apply product/Bruce 2nd motion/ Vote passed unanimously
* **Next Steps:??**
	+ Pick up RainGuard (Katie)/identify date for application

**Holiday Pop-Up Shop**

* **Proposal/Update:** Group
	+ Figure out location
	+ Arts Council needs to purchase grid walls and find a location to store them
* **Discussion:**
	+ Foyt Wine Vault, Wilcox
		- Wilcox would be the better location
		- Could the grid walls be stored at Wilcox or SMC?
* **Decisions: N/A**
* **Next Steps:**
	+ Chris to research grid wall prices
	+ Katie to reach out to Mel and Steve Wilcox for use of space

**Steampunk Artist Zoom Meeting**

* **Proposal/Update:**
	+ Artist would like to discuss his art included in town redevelopment
* **Discussion**:
	+ Meeting on Tuesday, Aug 9th at 5pm
	+ Jennifer Miller (SRC) and Todd Cook (economic development director) invited

**Interactive Murals on Main**

* **Proposal/Update:**
	+ Arts Council received grant for $10K to install 2 murals on Charlie Browns and City Dogs/Voom Room Building
* **Discussion:**
	+ Call to action to go out in late July and be open ended until artist is selected
	+ Budget for artist compensation is $8,000
		- Arts Council will be prepared to cover additional funding if needed to complete these murals